## Final Calculations
Calculations From Other Tabs
TCF |  | Technical Complexity Factor | 1.02
EF |  | Environmental Factor | 0.95
UUCP |  | Unadjusted Use Case Points | 25
AW |  | Actor Weighting | 9
Calculation of Use Case Points
UCP |  | Use Case Points | 32.946
Calculation of Estimated Effort
Ratio |  | Hours of Effort per Use Case Point | 20
Hours of Effort |  |  | 658.92 | HorasHombre | 658.92 | Dia | 1 | Mes | 1
|  |  |  | Hombre | 2 | Horas | 8 | dias | 20
| For additional guidance with this page, check out the following articles at Tyner Blain |  |  |  | 329.46 |  | 0.125 |  | 0.05 | 2.0591
Software Cost Estimation With Use Case Points - Introduction
Software Cost Estimation With Use Case Points - Final Calculations
Software Cost Estimation With Use Case Points - Free Excel Spreadsheet
Steps to Calculate Use Case Points
| 0 | For all tabs, enter values only in the highlighted cells
| 1 | Enter Technical Complexity Factors on the Technical tab
| 2 | Enter Environemental Factors on the Environmental tab
| 3 | Identify Use Cases on the Use Case tab
| 4 | Identify Actors on the Actor tab

## Technical
Technical Factor |  | Multiplier | Relative Magnitude (Enter 0-5) | Description
1 | Sistema distribuido | 2 | 5 | The architecture of the solution may be centralized or single-tenant , or it may be distributed (like an n-tier solution) or multi-tenant. Higher numbers represent a more complex architecture.
2 | Tiempos de respuesta críticos | 1 | 3 | The quickness of response for users is an important (and non-trivial) factor. For example, if the server load is expected to be very low, this may be a trivial factor. Higher numbers represent increasing importance of response time (a search engine would have a high number, a daily news aggregator would have a low number).
3 | Eficiencia del usuario | 1 | 3 | Is the application being developed to optimize on user efficiency, or just capability? Higher numbers represent projects that rely more heavily on the application to improve user efficiency.
4 | Procesos internos complejos | 1 | 3 | Is there a lot of difficult algorithmic work to do and test? Complex algorithms (resource leveling, time-domain systems analysis, OLAP cubes) have higher numbers. Simple database queries would have low numbers.
5 | Código reutilizable | 1 | 0 | Is heavy code reuse an objective or goal? Code reuse reduces the amount of effort required to deploy a project. It also reduces the amount of time required to debug a project. A shared library function can be re-used multiple times, and fixing the code in one place can resolve multiple bugs. The higher the level of re-use, the lower the number.
6 | Fácil de instalar | 0.5 | 0 | Is ease of installation for end users a key factor? The higher the level of competence of the users, the lower the number.
7 | Fácil de utilizar | 0.5 | 2 | Is ease of use a primary criteria for acceptance? The greater the importance of usability, the higher the number.
8 | Portable | 2 | 5 | Is multi-platform support required? The more platforms that have to be supported (this could be browser versions, mobile devices, etc. or Windows/OSX/Unix), the higher the value.
9 | Fácil de modificar | 1 | 3 | Does the customer require the ability to change or customize the application in the future? The more change / customization that is required in the future, the higher the value.
10 | Concurrencia | 1 | 3 | Will you have to address database locking and other concurrency issues? The more attention you have to spend to resolving conflicts in the data or application, the higher the value.
11 | Características de seguridad | 1 | 3 | Can existing security solutions be leveraged, or must custom code be developed? The more custom security work you have to do (field level, page level, or role based security, for example), the higher the value.
12 | Acceso a software de otras compañías | 1 | 3 | Will the application require the use of third party controls or libraries? Like re-usable code, third party code can reduce the effort required to deploy a solution. The more third party code (and the more reliable the third party code), the lower the number.
13 | Incluye facilidades de aprendizaje para el usuario | 1 | 0 | How much user training is required? Is the application complex, or supporting complex activities? The longer it takes users to cross the suck threshold (achieve a level of mastery of the product), the higher the value.
Calculated TCF |  |  | 1.02
For additional guidance with this page, check out the following articles at Tyner Blain
Software Cost Estimation With Use Case Points - Introduction
Software Cost Estimation With Use Case Points - Technical Factors
Software Cost Estimation With Use Case Points - Free Excel Spreadsheet

## Environmental
Environmental Factor |  | Multiplier | Relative Magnitude (Enter 0-5) | Description
1 | Familiarizado con RUP | 1.5 | 3 | ¿Cuánta experiencia tiene su equipo de trabajo en este ámbito? El dominio del proyecto será un reflejo de lo que el software está diseñado para llevar a cabo, no el lenguaje de implementación. En otras palabras, para un sistema de compensación de seguros escrito en Java, que se preocupan por la experiencia del equipo en el espacio de compensación de seguros - no cuánto java que han escrito. Los niveles más altos de experiencia reciben un número mayor.
2 | Experiencia en este tipo de aplicaciones | 0.5 | 3 | ¿Cuánta experiencia tiene su equipo con la aplicación. Esto sólo será relevante cuando se realizan cambios de una aplicación existente. Los números más altos representan más experiencia. Para una nueva aplicación, la experiencia de todo el mundo será 0.
3 | Experiencia en Orientación a Objeto | 1 | 3 | ¿Cuánta experiencia tiene su equipo tienen al OO? Puede ser fácil olvidar que muchas personas no tienen experiencia en programación orientada a objetos, si estás acostumbrado a tenerlo. Un proyecto impulsado caso de uso centrado en el usuario o tendrá una estructura inherentemente OO en la aplicación. Los números más altos representan más experiencia OO.
4 | Capacidad de liderazgo del analista | 0.5 | 4 | Como conocedor y capaz es la persona responsable de los requisitos? requisitos malas son el asesino número uno de los proyectos - Standish Group informa que el 40% y el 60% de los defectos provienen de malas requisitos. Los números más altos suponen una mayor habilidad y conocimiento.
5 | Motivación | 1 | 5 | El grado de motivación es su equipo? Los números más altos representan más motivación.
6 | Requisitos estables | 2 | 4 | Traductor Los cambios en los requisitos pueden causar incrementos en el trabajo. La forma de evitar esto es mediante la planificación para el cambio y la institución de un sistema de cronometraje para la gestión de dichos cambios. La mayoría de la gente no hace esto, y algunos de retrabajo serán inevitables. Los números más altos representan más cambio (o un sistema menos eficaz para la gestión del cambio).
7 | Trabajadores a tiempo parcial | -1 | 5 | Tenga en cuenta, el multiplicador para este número es negativo. Los números más altos reflejan los miembros del equipo que son a tiempo parcial, consultores externos y desarrolladores que están dividiendo su tiempo entre proyectos. El cambio de contexto y otros factores intangibles hacen estos miembros del equipo menos eficiente.
8 | Lenguaje de programación difícil de utilizar | -1 | 4 | Este multiplicador es también negativa. idiomas Harder representan números más altos. Creemos que la dificultad está en el ojo de la b-codificador (gemido). Java podría ser difícil para un programador FORTRAN. Piense en ello en términos de dificultad para su equipo, no dificultad abstracto.
Calculated EF |  |  | 0.95
For additional guidance with this page, check out the following articles at Tyner Blain
Software Cost Estimation With Use Case Points - Introduction
Software Cost Estimation With Use Case Points - Environmental Factors
Software Cost Estimation With Use Case Points - Free Excel Spreadsheet

## Use Case
Unadjusted Use Case Points |  | Multiplier | Number of Use Cases | Description
1 | Simple | 5 | 3 | El caso de Uso contiene menos de 3 transacciones
2 | Medio | 10 | 1 | El caso de Uso contiene de 4 a 7 transacciones
3 | Complejo | 15 | 0 | El caso de uso tiene más de 7 transacciones
Calculated UUCP |  |  | 25
Individual Use Cases |  | Multiplier | Use Case Name
1 | Simple | 5 | Mostrar cuestionario
2 | Simple | 5 | Ingreso al sistema
3 | Medio | 10 | Imprimir
4 | Simple | 5 | Eliminar, modificar, visualizar y crear contenido en la tablas disponibles
Insert additional rows above this row and copy the cell values to automatically update the counts of actors by type
For additional guidance with this page, check out the following articles at Tyner Blain
Software Cost Estimation With Use Case Points - Introduction
Software Cost Estimation With Use Case Points - Use Case Analysis
How to Write Good Use Case Names - 7 Tips
Software Cost Estimation With Use Case Points - Free Excel Spreadsheet

## Actor
Actor Summary |  | Multiplier | Number of Actors | Description
1 | Simple | 1 | 0 | Otro sistema externo, interactúa con el sistema a desarrollar mediante una interfaz de programación definida y conocida, (API, Application Programming Interface)
2 | Medio | 2 | 3 | Otro sistema externo que interactúa a través de protocolo (conjunto de reglas que especifican el intercambio de datos u órdenes durante la comunicación entre las entidades que forman parte de la red), Ej: TCP/IP.
3 | Complejo | 3 | 1 | Un usuario físico que interactúa a través de una interfaz gráfica de usuario.
Calculated AW |  |  | 9
Individual Actors |  | Multiplier | Actor Name
1 | Medio | 2 | Cliente
2 | Complejo | 3 | Administrador
3 | Medio | 2 | Recepcionista
4 | Medio | 2 | Terapeuta
Insert additional rows above this row and copy the cell values to automatically update the counts of actors by type
For additional guidance with this page, check out the following articles at Tyner Blain
Software Cost Estimation With Use Case Points - Introduction
Software Cost Estimation With Use Case Points - Actor Analysis
Software Cost Estimation With Use Case Points - Free Excel Spreadsheet